## Slide 1: Session 3: The Concept of Programme of Activities (PoA) Monitoring, Verification, CER Issuance and Post-registration changes for PoAs
Training-Workshop to support the
“Uganda Municipal Waste Compost Programme”
21 - 24 Oct 2013, Mukono Municipality, Uganda

## Slide 2: Outline
CDM PoA Cycle
CPA Inclusion in PoA
Monitoring of PoA
Monitoring Report and its elements
Key Elements of PoA Verification
Issuance of CDM PoA
Post Registration Changes (PRC)

## Slide 3: CDM PoA Cycle
CPA Inclusions
Monitoring report (MR
Verified/certified MR &
Request for issuance
Project design
National approval
Validation
Registration
Verification / certification
Issuance of Certified Emission Reductions (CERs)
Monitoring
DOE
CDM EB
Step
Who’s responsible
CME/ DOE
Coordinating and Managing Entity (CME)

## Slide 4: CPA Inclusion in PoA
PoA DD
PoA DD
Potential CPAs
CPA Inclusion checked by DOE and uploaded in CDM website
PoA at the time of registration
PoA DD
CPA Inclusion over the PoA Lifetime
PoA DD

## Slide 5: PoA Monitoring
CPA 2
CPA 3
CPA 4
Crediting Period : 21 years (maximum)
PoA Start Date
CPA Start Date
PoA Lifetime: 28 years
Verification of MP1
Monitoring Period 1 (MP 1)
Monitoring Period 2 (MP 2)
MP 3
MP 4, etc
Monitoring Report of MP1
UNFCCC
CERs
Verification and Certification Reports
-Final Monitoring Report
-Other relevant documents
-Request for Issuance of MP1
CPA 1
PoA Registration
Monitored by CME based on:
- Monitoring Plan of PoA DD
- Applied methodology
- current EB guidance
DOE
CPA 5
CPA 6
CPA 7, etc

## Slide 6: Monitoring Report
WHO?
The monitoring report form (CDM-MR) is intended to be completed by Coordinating and Managing Entity (CME).
WHY?
To present information related to the monitoring of one or more CPA during a monitoring period, and to support the DOE during the verification process.
WHAT?
Quantitative information such as reported numbers relating to the calculation of emission reductions achieved during the monitoring period by one or more CPA.
Qualitative information such as implementation and operational status, internal controls, procedures for calculations and data transfer, collection and recording.

## Slide 7: Elements of Monitoring Reports
Monitoring report contains the following section
  Section A: Description of project activity
  Section B: Implementation of project activity
  Section C: Description of monitoring system
  Section D: Data and parameters
  Section E: Calculations of emission reduction or GHG removals by sinks

## Slide 8: Monitoring Report for the PoA
Options
Option 1: A single monitoring report for all CPAs included in the PoA;
Option 2: Two MRs can be submitted for a single monitoring period but
  Each CPA shall only be included in one of the two MR and
  Two MRs shall together contain all monitoring results of all CPAs included in the PoA
MR should contain monitoring results of all CPA clearly separating the monitoring results of individual CPAs
In case of 2 MRs, DOE submits two separate issuance request.
The monitoring periods shall be consecutive.

## Slide 9: PoA verification
Verification of MP1
Monitoring Period 1 (MP 1)
Monitoring Period 2 (MP 2)
MP 3
MP 4, etc
Monitoring Report of MP1
UNFCCC
CERs
-Verification and Certification Reports
-Final Monitoring Report
-Other relevant documents
-Request for Issuance of MP1
CPA 1
CPA 2
CPA 3
CPA 4
CPA 5
CPA 6
PoA Lifetime: 28 years
Crediting Period : 21 years (maximum)
PoA Start Date
PoA Registration
Monitored by CME based on:
- Monitoring Plan of PoA DD
- Applied methodology
- current EB guidance
CPA Start Date
DOE
CPA 7, etc

## Slide 10: Verification of PoA
DOE verifies that emission reductions took place, in the amount claimed, according to approved monitoring plan for each CPA included in the PoA.
Years
GHG emissions (tCO2eq)
CPA1 Implementation
Emissions baseline
Beginning of monitoring period
Verification/ Certification of emission reductions
ADDITIONAL EMISSION REDUCTIONS
Emissions after the project
End of monitoring period
Notes: Verification is the independent review and ex post determination by the designated operational entity (DOE) of the monitored reductions in anthropogenic emissions by sources of greenhouse gases that have occurred as a result of a registered CDM project activity during the verification period.

## Slide 11: Key Elements of PoA Verification
1.
CPAs Implementation
2.
Monitoring Plan
3.
Monitoring Activities
4.
Calibration of equipment
5.
Calculations of emission reduction
Key Elements of Verification
Complete set of data
Cross checking of data
Use of default values
Calculations of baseline, project and leakage emission
Comparison of emission reduction
Notes: Project implementation - Compliance with the registered project design document e.g. implementation status, actual operation
Monitoring plan - Compliance with the monitoring methodology and applicable tools
Monitoring activities - Compliance with the registered monitoring plan e.g. monitoring of all parameters, sampling plan, management and operational system
Calibration - Compliance with the frequency requirements for measuring instruments
Calculation of emission reductions - Assessment of data and
  Availability of complete set of data
  Cross checking of the data
  Calculations of baseline, project and leakage emission
  Use of default values in the emission reduction calculation
  Comparison of emission reduction with the estimates in the registered PDD and explanation for any significant increase

## Slide 12: Verification Process
Publication of MR in UNFCCC website
Desk Review of monitoring report
Site visit and Interviews
Draft of technical review
Feedback and clarifications
Receive responses
Final Technical Review
Request for Issuance
Submission of MR to DOE
DOE submits the Request for Issuance with the following documents:
  Verification Report
  Certification Report
  Final Monitoring Report
  Other relevant supporting documents
  Request for Issuance of MP1

## Slide 13: Issuance of CDM PoA
Completeness Check (CC): Check the completeness and consistency of the documents
Information and Reporting Check (I&RC): Check in accordance with the I&RC Checklist for request for issuance published in UNFCCC CDM website.
Summary Note (SN): Secretariat prepare and send the summary note to EB
Commencement
CC finalized
7 days
I&RC finalized
23 days
Automatic Issuance
28 days
Summary Note preparation
14 days
Period to Request for Review
Request for Review by a party involved in PoA or at least 3 EB members
72 days

## Slide 14: CME change in PoA
What happens if the CME of the PoA changes after the registration of the PoA?
  New letter of authorization from each of the host party
  Confirmation from the new CME that PoA will be developed and implemented with the same set framework in registered CDM-PoA-DD
  Compliance of the new CME with the requirements of the PoA management system as described in the POA DD
CME submits the above documents to the DOE for validation.

## Slide 15: Post Registration Change of PoA
All post registration changes applicable to CDM Project Activity are applicable to the CDM PoA also
PoA Specific Changes
  Addition of host Parties
  Updates to the eligibility criteria
  Inclusion of new specific case CPA-DDs
  Removal of methodologies from the registered PoA.
Notes: Changes to programme boundary to expand geographical coverage or to include additional host Parties;
Updates to the eligibility criteria (e.g. to implement changes decided by the Board if an issue related to environment integrity is identified);
Addition of specific case CPA-DDs corresponding to generic CPA-DDs for which a specific case CPA-DD has not been submitted at the time of request for registration of the PoA;
Removal of methodologies from the registered PoA.
For the PRC of PoA, the CME shall update the eligibility criteria for inclusion of CPAs in the PoA to reflect the change, and include them in new versions of PoA-DD and generic CPA-DD

## Slide 16: Timeline for processing PoA PRC – Prior Approval
Completeness Check (CC): Check the completeness and consistency of the documents in accordance with the completeness checklist for request for PRC published in UNFCCC CDM website.
Summary Note (SN): Secretariat prepare and send the summary note to EB
Commencement
CC finalized
7 days
14 days
Approve the changes
Summary Note preparation
20 days
Reject the changes
41 days
Objection period by EB members

## Slide 17: Thank you
Thank you