## Slide 1: Planning for the International Assessment and Review process
First technical workshop on the revision of the guidelines for the review of biennial reports and national communications, including national inventory reviews for developed country Parties. Bonn, 7 October 2013

## Slide 2: IAR cycle based on decision 2/CP.17
  1 January 2014 – submission of first biennial reports
  1 March 2014 (two months after submission (para. 25)) – 1st round of IAR starts with the technical review of BRs:
    In accordance with existing and revised guidelines and procedures (para. 6, Annex II);
    Technical review report based on existing reporting standards (para. 7, Annex II);
  Multilateral Assessment builds on the published BR review report as major input (para. 8, Annex II);
  Any Party can submit written questions in advance of the MA (para. 10, Annex II);
  The Party under assessment should respond to those questions within two months (ibid.);
  The secretariat will compile the Q+As and publish them on the UNFCCC website (ibid.);
1st IAR cycle

## Slide 3: IAR cycle based on decision 2/CP.17
  During the SBI session, all AI Parties will undergo the assessment.
  IAR output record (para. 30, and para. 11 of Annex II):
    Secretariat to prepare a summary report of the SBI;
    Any other observations by the reviewed Party submitted two months after the SBI.
  Key steps and involvement:
1st IAR cycle
 | BR submission | Technical review | Multilateral assessment
Party under IAR |  |  | 
Other Parties |  |  | 
ERT |  |  | 
Secretariat |  |  | 

## Slide 4: IAR cycle based on decision 2/CP.17
Technical Review (17 weeks)
[Preparation of review (4-8 weeks before RW)]
Multilateral Assessment (14 weeks)
Preparation of MA (min.12 weeks before SBI)
IAR Party Record (9 weeks after SBI)
SBI summary report (9 weeks)
Review week (1 week)
Finalizing review report (16 weeks after review week)
Questions by Parties (min. 4 weeks)
Answers by Parties (min. 8 weeks)
MA during SBI (2 weeks)
Observations by the reviewed Party (8 weeks after SBI)
Review report
Q+As by Parties
Detailed 1st IAR cycle

## Slide 5: IAR cycle based on decision 2/CP.17
Detailed 1st IAR cycle
2016
2015
2014
1st BR and 6th NC submission
2nd BR submission
1 March, beginning of 1st IAR
Technical review (17 weeks)
Preparation IAR (12 weeks)
IAR Record (9 weeks)
SBI (2 weeks)
IAR process (40 weeks)
prep

## Slide 6: IAR cycle based on decision 2/CP.17
Detailed 1st IAR cycle
2016
2015
2014
SBI 40
SBI 41
SBI 42
SBI 43
1st BR and 6th NC submission
2nd BR submission
1 March, beginning of 1st IAR
IAR process
RW 29 weeks before SBI
RR 12 weeks before SBI
Record 9 weeks after SBI
Notes: SBI 41: 3-14 Dec 2014 (beginning Mai, Sept)

## Slide 7: IAR cycle based on decision 2/CP.17
2016
2015
2014
SBI 40
SBI 41
SBI 42
SBI 43
1st BR and 6th NC submission
2nd BR submission
1 March, beginning of 1st IAR
IAR process
RW 29 weeks before SBI
RR 12 weeks before SBI
Record 9 weeks after SBI
Detailed 1st IAR cycle
Notes: SBI 42: 3-14 June 2014 (beginning Nov, March)

## Slide 8: IAR cycle based on decision 2/CP.17
2016
2015
2014
SBI 40
SBI 41
SBI 42
SBI 43
1st BR and 6th NC submission
2nd BR submission
1 March, beginning of 1st IAR
IAR process
RW 29 weeks before SBI
RR 12 weeks before SBI
Record 9 weeks after SBI
Detailed 1st IAR cycle
Notes: SBI 43: 2-13 Dec 2015 (beginning Mai, Sept)

## Slide 9: Planning for 1st IAR cycle – challenge – continuous review activities puts pressure on Parties and the secretariat
  For the multilateral assessment of Parties working group session under SBI 41 (Dec 2014)
    Review week by April 2014
    Review report by August 2014
    IA record by Jan 2015
  For the multilateral assessment of Parties at SBI 42 (June 2015)
    Review week by October 2014
    Review report by February 2015
    IA record by July 2015
  For the multilateral assessment of Parties at SBI 43 (Dec 2015)
    A few remaining Parties, if needed.
Planning for 1st IAR cycle
Notes:   2/CP.17 recognizes the need to have an efficient, cost-effective and practical international assessment and review process which does not impose an excessive burden on Parties and on the secretariat (preambular)
  2/CP.17 requests the secretariat to enhance coordination between different review processes in such a way as to ensure effective and efficient processes and procedures (para. 29)

## Slide 10: Planning for 1st IAR cycle – challenge - increasing demand for review experts
  Increasing number of experts is needed
    144 experts in NC5 review cycle (in-country and centralized reviews)
  Pressure on AI Parties:
    Financial resources to fund experts;
    In-kind contribution by experts (15-20 working day per review/per expert)
    Organizational efforts for in-country reviews and mobilization of resources for reviews
  Enhancing competence of experts
  Competing review processes: annual and periodic (the same experts are involved in the review activities. Participation in both GHG inventory and BR/NC reviews in 2014 implies up to 40 working days away from the expert’s ordinary work. This hardly possible for many experts)

## Slide 11: Conclusions
  Continuous IAR activities in 2014 -2015 puts huge pressure on resources (time, people and financial) of Parties and the secretariat:
  Challenges due to:
    Launching of a new process
    Tight schedule for IAR
    The need for increasing number of experts;
    The need for qualified/trained experts.
  Need to consider these challenges while discussing format of the BR/NC reviews.